## Quality Report
Quality Report
Defect (No of Def/KLOC)
# | Product | Quality Control Activity | Plan | Actual
1 | Test
|  | Unit Test | 3-4 | 3
|  | Integration Test | 2-3 | 1
|  | System Test | 4-6 | 9
2 | Requirements | Review | 10 | 6
3 | Design | Review | 15 | 21
4 | Code | Review | 30 | 16
5 | Project Plan | Review | 10 | 2
6 | Project Schedule | Review | 10 | 6
7 | Test Plan | Review | 10 | 4
8 | Other document | Review | 15 | 11
Total |  |  | 42-48 | 79
Test Report
Refer to Test Report in TC Template