## Risk register
Risk Register for Dandelion System
Prepared by: |  | TuanHA |  |  | Date: | 2016-09-09
No | Rank | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contigency plan | Fallback plan | Potential Responses | Probability | Impact | Status
1 | 3 | Conflict among team members |  | People | Team member doesn't understand each others | Has issue inside team | Plan some team buildings to improve teammate | Have a meeting to resolve conflict problem | Kick member out or switch to another team. |  | medium | high
2 | 4 | Requirement is not fit with program after project is started |  | Process | SRS not good (not realistic, not feasibility, not meet customer needs) | Project team cannot develop the system as desciption in SRS. | Requirement should be paid a lot of attention. SRS should be reviewd carefully by PM and the supervisor. | With each requirement changes, the project tema should have a meeting to analysis the change requests and take actions. | Re-estimate and update plan. |  | high | medium
3 | 5 | Team member do not meet the deadline |  | Process | Undisciplined and habit of team member, loose management | Have a deadline | Setting rule and minus of do not meet the deadline: lost money and named at meeting minute. | Punish the member do not meet the deadline. Working over time. | Ask for help from out of team, supervisors. |  | medium | medium
4 | 7 | Inability to verify/validate products against requirements. |  | Process |  | Inability to verify/validate products against requirements. | Print out the result to check by normal eyes. Debug into code to see how the code is running | Print out the result to check by normal eyes. Debug into code to see how the code is running | Ask for help from supervisors |  | medium | low
5 | 6 | The server has defective parts. |  | Technology | Defective power supply… | Server is down… | Ensure the supplier provides with the adequate warranties. | Replace or fix the defective parts quickly. | Buy a new one. |  | low | medium
6 | 10 | Delivery project doesn’t meet requirement |  | Process | Team member not understand requirement | Can't delivery project | Teamlead have to review sourcecode and follow requirement | Fix in next version | Extend dealine |  | medium | low
7 |  | Loss data, source code before uploading data to server because of careless |  | People - Process | Member commit process is wrong or maybe server occur some error | Losing code or conflix code with server | All members have to know how to use tortoiseGit and doing the right process | Revert code to lastest version. | Revert code to lastest version and re-coding the losing code |  | medium | high
8 |  | Coding environment or assets is not enough |  | Technology |  | can't not continue coding | fully prepare anything to code | immediately prepare and continue coding |  |  | low | low
9