## Cover
Quality Management System
WS_Test Report
WS
Version : 1.0
Document Control information
Issue Date: | 2015-09-12
Issue Status: | Approved
Author: | Tạ Ngọc Duy
Reviewer information | Đỗ Văn Tuấn | Member | Required
Approver information
Document Revision History
Date | Version | Description | Revised by
2016-09-12 | 1 | Create document | Đào Trọng Nghĩa
Note on B11: Add more reviewers as necessary
Note on B13: Add more approvers here as necessary

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 30TC/KLOC | 3 -4 defects/KLOC | 340 | 1 defects/KLOC | 100% | 100% | 0%
Integration Test | 30TC/KLOC | 2 - 3 defects/KLOC | 426 | 1 defects/KLOC | 100% | 100% | 0%
System Test | 50TC/KLOC | 4 -6 defects/KLOC | 536 | 8 defects/KLOC | 100% | 100% | 0%
Total | 110TC/KLOC | 10-15 defects/KLOC | 1302 | 10 defects/KLOC | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2
| Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A
Unit Test | 337 | 3 | 0 | 0 | 340 | 0 | 0 | 0
Integration Test | 414 | 13 | 0 | 0 | 426 | 0 | 0 | 0
System Test | 510 | 42 | 6 | 4 | 536 | 0 | 0 | 0
Total | 1261 | 58 | 6 | 4 | 1302 | 0 | 0 | 0
Defect report
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 3 | 0% | 0% | 0%
Medium | 13 | 100% | 0% | 0%
Low | 42 | 100% | 0% | 0%
Total | 58 | 100% | 0% | 0%