## Cover
TEST CASE
Project Name | WingS |  |  | Creator | DuyTN
Project Code | WS |  |  | Reviewer/Approver | NghiaDT
Document Code | WS_System Test Case_v1.0 |  |  | Issue Date | 28/10/2016
|  |  |  | Version | 1.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
28/10/2016 | 1.0 |  | A
Note on E11: *A: Add M: Modify D: Delete

## Test Report
TEST REPORT
Project Name | WingS |  | Creator |  | DuyTN
Project Code | WS |  | Reviewer/Approver |  | NghiaDT
Document Code | WS_System Test Report_v1.0 |  | Issue Date |  | ../../2016
Notes
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | Common | 0 | 0 | 68 | 0 | 68
2 | Managa Event | 104 | 2 | 4 | 0 | 110
3 | Manage Thread | 66 | 0 | 2 | 0 | 68
4 | Organization | 40 | 0 | 0 | 0 | 40
5 | User Profile | 36 | 0 | 0 | 0 | 36
6 | Donate | 30 | 0 | 0 | 0 | 30
7 | Message | 36 | 0 | 0 | 0 | 36
8 | Admin module | 1 | 0 | 141 | 0 | 142
| Sub total | 313 | 2 | 215 | 0 | 530
| Test coverage |  | 59.434 | %
| Test successful coverage |  | 59.0566 | %

## Test case List
TEST CASE LIST
Project Name |  | WingS
Project Code |  | WS
Test Environment Setup Description |  | List enviroment requires in this system 1. Server: 2. Database server: SQL Server 2012 3. Browser: Google Chrome 53, Mozzila Firefox 30 4. Operation System: Window 8.1 Professional 64 bit
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Common | Common
2 | Manage event | Managa Event
3 | Manage Thread | Manage Thread
4 | Organization | Organization
5 | User Profile | User Profile
6 | Donate | Donate
7 | Message | Message
8 | Admin module | Admin module

## Message rule
Message Rules
No | Description Vietnam | Description English
MS01 | Bạn chưa nhập Email
MS02 | Email sai định dạng
MS03 | Bạn chưa nhập tài khoản hoặc email
MS04 | Bạn chưa nhập mật khẩu
MS05 | Mật khẩu không giống nhau
MS06 | Sai mật khẩu hoặc tài khoản không tồn tại
MS07 | Tên tài khoản từ 8 đến 20 ký tự
MS08 | Tên tài khoản tối đa 20 kí tự
MS09 | Tên tài khoản chỉ gồm chữ và số
MS10 | Bạn chưa nhập tên
MS11 | Tài khoản bị khóa hoặc chưa xác nhận Email!
MS12 | Mật khẩu phải từ 8 đến 50 kí tự
MS13 | Tên đầy đủ tối thiểu 6 kí tự
MS14 | Tên dự án tối thiểu 10 kí tự
MS15 | Tên dự án tối đa 60 kí tự
MS16 | Bạn chưa nhập tên dự án
MS17 | Phải là chữ số và lớn hơn 1,000,000
MS18 | Bạn chưa nhập số tiền gây quỹ
MS19 | Xin hãy xem lại trang thông tin cơ bản, các trường (kể cả ảnh dự án) PHẢI được điền đầy đủ và hợp lệ Xin hãy xem lại trang câu chuyện! Các trường PHẢI được nhập đầy đủ (trừ video)
MS20 | Mô tả ngắn phải từ 30 đến 135 kí tự
MS21 | Bạn chưa nhập mô tả ngắn
MS22 | Mô tả ít nhất 135 kí tự
MS23 | Tiêu đề ít nhất 10 ký tự
MS24 | Mô tả ít nhất 30 kí tự
MS25 | Câu hỏi ít nhất 10 ký tự
MS26 | Câu trả lời hỏi ít nhất 10 ký tự
MS27 | Bình luận tối thiểu từ 10 đến 500 kí tự.
MS28 | Email này đã được sử dụng
MS29 | Tên đầy đủ tối đa 20 kí tự
MS30 | Tài khoản không tồn tại
MS31 | Bạn đã gửi báo cáo thành công, cảm ơn bạn đã dùng dịch vụ của chúng tôi.
MS30 | Nhập lại mật khẩu không được để trống
MS31 | Nhập lại mật khẩu không giống
MS32 | Đã cập nhật thông tin thành công
MS33 | Vui lòng điền vào trường này
MS34 | Bạn đã gửi tin nhắn thành công, hãy kiểm tra tại Tin nhắn

## Common
Back to Test Report | [8 empty] | Defects
Module Code | Common Module | [7 empty] | Pass
Test requirement | This test cases were created to test Common module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untested
0 | 0 | 68 | 0 | 68 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 30 | Test date | Note
Scroll group
[Common Module-2] | User click "Back to top" icon button | 1. Go to wings.com 2. Click "Back to top" icon button | 1. Go to wings.com 2. Scroll to top page
[Common Module-3] | User click "Go to bottom" icon button | 1. Go to wings.com 2. Click "Go to bottom" icon button | 1. Go to wings.com 2. Scroll to bottom page
[Common Module-4] | User click "f5" button | 1. Go to wings.com 2. Click "f5" button | 1. Go to wings.com 2. This page is refreshed
[Common Module-5] | User click "Refresh" icon button | 1. Go to wings.com 2. Click "Refresh" icon button | 1. Go to wings.com 2. This page is refreshed
Search
[Common Module-7] | User go to search page succesfull | 1. Go to wings.com 3. Click "Search" icon | 1.Homepage is displayed 2. Search page is displayed
[Common Module-8] | User search an other user with no data result | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Người dùng" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with no record
[Common Module-9] | User search an other user with 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Người dùng" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 10 records in 1 page
[Common Module-10] | User search an other user more than 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Người dùng" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 2 pages or more
[Common Module-11] | User search an other account with no data result | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Tài khoản" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with no record
[Common Module-12] | User search an other account with 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Tài khoản" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 10 records in 1 page
[Common Module-13] | User search an other account more than 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "DuyTN" into search text box 4. Choose "Tài khoản" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with with 2 pages or more
[Common Module-14] | User search event with no data result | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Sự kiện" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with no record
[Common Module-15] | User search event with 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Sự kiện" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 10 records in 1 page
[Common Module-16] | User search event more than 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Sự kiện" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 2 pages or more
[Common Module-17] | User search thread with no data result | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Thảo luận" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with no record
[Common Module-18] | User search thread with 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Thảo luận" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 10 records in 1 page
[Common Module-19] | User search thread more than 10 data results | 1. Go to wings.com 2. Click on "Search" icon 3. Input "Chidrent" into search text box 4. Choose "Thảo luận" 5. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 2 pages or more
[Common Module-20] | User search Organization with no data result | 1. Input "DuyTN" into search text box 2. Choose "Tổ chức" 3. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with no record
[Common Module-21] | User search Organization with 10 data results | 1. Input "DuyTN" into search text box 2. Choose "Tổ chức" 3. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 10 records in 1 page
[Common Module-22] | User search Organization more than 10 data results | 1. Input "DuyTN" into search text box 2. Choose "Tổ chức" 3. Press Enter | 4. This name is displayed in search text box 5. Search Result page is displayed with 2 pages or more
[Common Module-23] | User search a blank | 1. Input "" into search text box 2. Choose 1 search type and click Search | 1.Homepage is displayed 2. "" is displayed in search text box 3. Search Result page is displayed with all exist event
[Common Module-24] | User search unusual characters | 1. Input unusual [!$#$@] characters into search text box 2. Click Search or press Enter | 1. Input data is displayed in search text box 2. Search Result page is displayed
[Common Module-25] | User search with max length keyword | 1. Input [maxlength] characters into search text box 2. Click Search or press Enter | 1. Input data is displayed in search text box 2. Search Result page is displayed
[Common Module-26] | User search with over max length keyword | 1. Input [maxlength+1] characters into search text box 2. Click Search or press Enter | 1. First [maxlength] of input data is displayed in search text box 2. Search Result page is displayed
Homepage Display
[Common Module-28] | Test Homepage view in 1366x768 screen | 1. Go to wings.com | 1. Homepage is displayed includes: - Header - Slider - Category - Top Event - Top Thread - Top organizations - Footer
[Common Module-29] | Test Logo image button | 1. Click Website logo | 1. Homepage is displayed
[Common Module-30] | Test search page view | 1. Click Search bar | 1. Search page is displayed include: - Header - Search bar: + Search text box + Mutiselect category
[Common Module-31] | Test Login View | 1. Enter the website: http://www.wings.com 2. Click Login button on Homepage | 1. The Home page is displayed 2. The Login page is displayed and "Login" form located in the login page with the following information: - Login with Facebook button - Account or Email Address textbox - Password field - Remember login checkbox - Login button - Forgot your password hyperlink - Sign up new hyperlink
[Common Module-32] | Test Register View | 1. Enter the website: http://www.wings.com 2. Click on Register button on Home page | 1. The Homepage is displayed 2. The Register page is displayed and "Register" form located in the login page with the following information: + Login with facebook button + Username field + Password field + Re-enter password field + Email field + Full Name field + Sign up button + Log in new hyperlink
[Common Module-33] | Test avatar menu view | 1. Hover or Click Avatar button in Header | 1. User menu is displayed include: - Message menu item - Noticification menu item - Profile menu item - Logout menu item
[Common Module-34] | Test slider User click Left/Right button | 1. Click Left/Right button in Slider | 1. Item Slider switch another slider.
[Common Module-35] | User click view event button | 1. Click View event button in Homepage | 1. Event detail page is displayed
[Common Module-36] | User click view thread button | 1. Click View thread button in Homepage | 1. Thread detail page is displayed
[Common Module-37] | User click view organization button | 1. Click View organization button in Homepage | 1. Organization detail page is displayed
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Manage Event
Back to Test Report
Module Code | Manage Event | [7 empty] | Pass
Test requirement | This test cases were created to test Manage Event module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
104 | 2 | 4 | 0 | 110 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[Manage Event-2] | Go to Event page when login | 1. Login wings.com with registered account 2. Click on Event tab | 2. Event page is displayed and |  | Pass | Pass | 2016-12-03
[Manage Event-3] | View Event page with no event when login | 1. Login wings.com with registered account 2. Click on Event tab | 1. Homepage is displayed 2. Event page is displayed with no event |  | Pass | Pass | 2016-12-03
[Manage Event-4] | View Event page with 5 events when login | 1. Login wings.com with registered account 2. Click on Event tab | 1. Homepage is displayed 2. Event page is displayed with 4 events and Load more icon displayed |  | Pass | Pass | 2016-12-03
[Manage Event-5] | Test click "Load more" button on event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click load more | 1. Homepage is displayed 2. Event page is displayed with 4 events 3. 4 events are loaded and Load more icon displayed |  | Pass | Pass | 2016-12-03
[Manage Event-6] | Test click "Load more" button 2 times on event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click load more 2 times | 1. Homepage is displayed 2. Event page is displayed with 4 events 3. 8 events are loaded and Load more icon displayed |  | Pass | Pass | 2016-12-03
[Manage Event-7] | Test click "Load more" button until no more event left | 1. Login wings.com with registered account 2. Click on Event tab 3. Click load more button till no more event left | 1. Homepage is displayed 2. Event page is displayed with 4 events 3. All event are displayed and "Load more" button is not displayed |  | Pass | Pass | 2016-12-03
[Manage Event-8] | Check Click on "Order by" on Event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on "Order by" button | 3. Display the sorting criterias |  | Pass | Pass | 2016-12-03
[Manage Event-9] | Check Click on "Order by" on Event page and choose 1 | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on "Order by" button and choose 1 | 3. Display the sorting criterias dropdowlist 4. The dropdownlist closed and the criteria which chosen is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-10] | Check Click on "Sociocultural" link on Event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on ""Sociocultural" link | 3. All events are sorting by Sociocultural type |  | Pass | Pass | 2016-12-03
[Manage Event-11] | Check Click on "Education" link on Event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on ""Education"" link | 3. All events are sorting by Education type |  | Pass | Pass | 2016-12-03
[Manage Event-12] | Check Click on "Medical" link on Event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on "Medical" link | 3. All events are sorting by Medical |  | Pass | Pass | 2016-12-03
[Manage Event-13] | Check Click on "Other" link on Event page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on "Other" link | 3. Redirect to event order by page |  | Pass | Pass | 2016-12-03
[Manage Event-14] | Check Event title on event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page with title same with in database |  | Pass | Pass | 2016-12-03
[Manage Event-15] | Check Event creator on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page - Display creator name of Event |  | Pass | Pass | 2016-12-03
[Manage Event-16] | Check Click Event creator on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on Creator name of Event | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Move to Organization profile page of creator |  | Pass | Pass | 2016-12-03
[Manage Event-17] | Check Like button on Event detail page when user did not like this Event before | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on Like button | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Change color of like button and number of like increase 1 |  | Pass | Pass | 2016-12-03
[Manage Event-18] | Check Like button on Event detail page when user already liked | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on Like button | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Change color of like button and number of like decrease 1 |  | Pass | Pass | 2016-12-03
[Manage Event-19] | Check Share button on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on Share button | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Redirect to confirm share post of facebook |  | Pass | Pass | 2016-12-03
[Manage Event-20] | Check Event content on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page - Display content of Event in Content tab |  | Pass | Pass | 2016-12-03
[Manage Event-21] | Check Event picture on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on Picture tab | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Display pictures of Event in Pictures tab |  | Pass | Pass | 2016-12-03
[Manage Event-22] | Check Event timeline on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on timeline tab | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Display timeline of Event in timeline tab |  | Pass | Pass | 2016-12-03
[Manage Event-23] | Check Event donate on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on donate tab | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Display donate of Event in donate tab |  | Pass | Pass | 2016-12-03
[Manage Event-24] | Check Event contact on Event detail page | 1. Login wings.com with registered account 2. Click on Event tab 3. Click on a Event 4. Click on contact tab | 1. Homepage is displayed 2. Event page is displayed 3. Display Event detail page 4. Display contact of Event in contact tab |  | Pass | Pass | 2016-12-03
[Manage Event-25] | Check number comment of event on event detail page | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page - Display number comment of event |  | Pass | Pass | 2016-12-03
[Manage Event-26] | Check all comment of event on event detail page | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page - Display all comment of event |  | Pass | Pass | 2016-12-03
[Manage Event-27] | Check Send comment on event detail page | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Write comment and press Enter | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display comment |  | Pass | Pass | 2016-12-03
[Manage Event-28] | Check Like comment button on event detail page when user did not like this event before | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on Like comment button | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Change color of like comment button and number of like increase 1 |  | Pass | Pass | 2016-12-03
[Manage Event-29] | Check Like button on event detail page when user already liked | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on Like comment button | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Change color of like comment button and number of like decrease 1 |  | Pass | Pass | 2016-12-03
[Manage Event-30] | Check Reply comment button on event detail page | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on Reply comment button | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display comment text for user |  | Pass | Pass | 2016-12-03
[Manage Event-31] | Check Send reply comment on event detail page | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on Reply comment button 5. Write comment and press Enter | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display sub comment text for user 5. Display reply comment |  | Pass | Pass | 2016-12-03
[Manage Event-32] | Check "Report" button on event detail page when user already reported before | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on "Report" button | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display pop-up and notice that user already reported |  | Pass | Pass | 2016-12-03
[Manage Event-33] | Check "Send Report" button in Report pop-up | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on "Report" button 5. Choose 1 reason and click send | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display pop-up with reasons. 5. Pop-up is closed and notice that report successful |  | Pass | Pass | 2016-12-03
[Manage Event-34] | Check "Report" button in Report pop-up when user already reported before | 1. Login wings.com with registered account 2. Click on event tab 3. Click on a event 4. Click on "Report" button | 1. Homepage is displayed 2. event page is displayed 3. Display event detail page 4. Display pop-up with message: [MS31] |  | Pass | Pass | 2016-12-03
[Manage Event-35] | Go to Creat Event page when login | 1. Login wings.com with registered account 2. Click on Create Event | 2. Create Event page is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-36] | Go to Creat Event page and check Content tab | 1. Login wings.com with registered account 2. Click on Create Event | 2. Create Event page is displayed - Content tab is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-37] | Go to Creat Event page and check Timeline tab | 1. Login wings.com with registered account 2. Click on Create Event 3. Click on Timeline tab | 2. Create Event page is displayed 3. Timeline tab is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-38] | Go to Creat Event page and check Picture tab | 1. Login wings.com with registered account 2. Click on Create Event 3. Click on Pictures tab | 2. Create Event page is displayed 3. Picture tab is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-39] | Upload Event pictures | 1. Login wings.com with registered account 2. Click on Create Event 3. Click on Timeline tab 4. Click on upload pictures | 2. Create Event page is displayed 3. Picture tab is displayed 4. Pictures is uploaded |  | Pass | Pass | 2016-12-03
[Manage Event-40] | Create Event successful | 1. Login wings.com with registered account 2. Click on Create Event 3. Fill all information and click Create | 2. Event page is displayed 3. Event created and redirect to event detail |  | Pass | Pass | 2016-12-03
[Manage Event-41] | Review creator of recent event created | 1. Login wings.com with registered account 2. Click on Create Event 3. Fill all information and click Create | 2. Event page is displayed 3. Event created and redirect to event detail - Display name of event's creator |  | Pass | Pass | 2016-12-03
[Manage Event-42] | Review date created of recent event created | 1. Login wings.com with registered account 2. Click on Create Event 3. Fill all information and click Create | 2. Event page is displayed 3. Event created and redirect to event detail - Display date created of event's creator |  | Pass | Pass | 2016-12-03
[Manage Event-43] | Review content of recent event created | 1. Login wings.com with registered account 2. Click on Create Event 3. Fill all information and click Create 4. Click on Content tab 5. Click on timeline tab 6. Click on Pictures tab | 2. Event page is displayed 3. Event created and redirect to event detail 4. Content of event is displayed 5. Timeline of event is displayed 6. Pictures of event is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-44] | Go to Edit Event page | 1. Login wings.com with registered account 2. Click on Avatar menu -> Your organization 3. Click on an event 4. Click on Edit event | 2. Event tab is displayed 3. Created event page is displayed 4. Edit event page is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-45] | Go to Edit Event page | 1. Login wings.com with registered account 2. Click on Avatar menu -> Your organization 3. Click on an event 4. Click on Edit event | 2. Event tab is displayed 3. Created event page is displayed 4. Edit event page is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-46] | Edit Event page successful | 1. Login wings.com with registered account 2. Click event tab 3. Click on a created event 4. Click on Edit event 5. Edit event and click "Save" button | 2. Event tab is displayed 3. Created event page is displayed 4. Edit event page is displayed 5. Edit event page is closed and move to event detail |  | Fail | Fail | 2016-12-03
[Manage Event-47] | Review creator of recent event edited | 1. Login wings.com with registered account 2. Click event tab 3. Click on a created event 4. Click on Edit Event 5. Edit event and click "Save" button | 2. Event tab is displayed 3. Created event page is displayed 4. Edit event page is displayed 5. Edit event page is closed and move to event detail - Display name of event's creator as before |  | Untesed | Untesed | 2016-12-03
[Manage Event-48] | Review content of recent event edited | 1. Login wings.com with registered account 2. Click event tab 3. Click on a created event 4. Click on Edit event 5. Edit event and click "Save" button | 2. Event tab is displayed 3. Created event page is displayed 4. Edit event page is displayed 5. Edit event page is closed and move to event detail - Display content of event as edited |  | Untesed | Untesed | 2016-12-03
[Manage Event-49] | View chat room in an event | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event | 3. Event detail page is displayed - Room chat pop up is displayed on right corner of page |  | Pass | Pass | 2016-12-03
[Manage Event-50] | Show up room chat | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on header of chat room | 3. Event detail page is displayed 4. Room chat pop up is displayed |  | Pass | Pass | 2016-12-03
[Manage Event-51] | Minimize room chat by click on header of Room chat pop-up | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on header of chat room | 3. Event detail page is displayed 4. Room chat pop up is minimized |  | Pass | Pass | 2016-12-03
[Manage Event-52] | Minimize room chat by click on Minimize button of Room chat pop-up | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on Minimize button of chat room | 3. Event detail page is displayed 4. Room chat pop up is minimized |  | Pass | Pass | 2016-12-03
[Manage Event-53] | Close room chat pop-up | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on Close button of chat room | 3. Event detail page is displayed 4. Room chat pop up is disappear |  | Pass | Pass | 2016-12-03
[Manage Event-54] | Enter room chat successful with no message on it | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on header of chat room 5. Click Enter chat room | 3. Event detail page is displayed 4. Room chat pop up is displayed 5. Room chat content is displayed with no message |  | Pass | Pass | 2016-12-03
[Manage Event-55] | Enter room chat successful with messages on it | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on header of chat room 5. Click Enter chat room | 3. Event detail page is displayed 4. Room chat pop up is displayed 5. Room chat content is displayed with messages display on it |  | Pass | Pass | 2016-12-03
[Manage Event-56] | Send message in chat room | 1. Login wings.com with registered account 2. Click event tab 3. Click on an event 4. Click on header of chat room 5. Click Enter chat room 6. Write message and press Enter | 3. Event detail page is displayed 4. Room chat pop up is displayed 5. Room chat content is displayed 6. Message sent and display on chat room content. |  | Pass | Pass | 2016-12-03
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Manage Organization
Back to Test Report
Module Code | Manage Organization | [7 empty] | Pass
Test requirement | This test cases were created to test Manage organization module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
40 | 0 | 0 | 0 | 40 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[Manage Organization-2] | Go to Organization page when login | 1. Login wings.com with registered account 2. Click on Organization tab | 2. Organization page is displayed |  | Pass | Pass | 2016-12-08
[Manage Organization-3] | Check tab focus when user viewing Organization page | 1. Login wings.com with registered account 2. Click on Organization tab | 2. Organization page is displayed and tab focus Organization |  | Pass | Pass | 2016-12-08
[Manage Organization-4] | View Organization page with no Organization | 1. Login wings.com with registered account 2. Click on Organization tab | 1. Homepage is displayed 2. Organization page is displayed with no Organization |  | Pass | Pass | 2016-12-08
[Manage Organization-5] | View Organization page with 10 Organizations | 1. Login wings.com with registered account 2. Click on Organization tab | 1. Homepage is displayed 2. Organization page is displayed with 8 Organizations and Load more icon displayed |  | Pass | Pass | 2016-12-08
[Manage Organization-6] | Test Click Load more in event page and with 8 events | 1. Login wings.com with registered account 2. Click on Organization tab | 1. Homepage is displayed 2. Organization page is displayed 8 events and button "Load more" is not displayed |  | Pass | Pass | 2016-12-08
[Manage Organization-7] | View Organization detail | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page |  | Pass | Pass | 2016-12-08
[Manage Organization-8] | Check Organization Name on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page with name same with in database |  | Pass | Pass | 2016-12-08
[Manage Organization-9] | Check Organization information on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page |  | Pass | Pass | 2016-12-08
[Manage Organization-10] | View list event of Organization with no event created | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page - No event display |  | Pass | Pass | 2016-12-08
[Manage Organization-11] | View list event of Organization with no event created | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page - No event display |  | Pass | Pass | 2016-12-08
[Manage Organization-12] | View list event of Organization with 5 events created | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page - 4 events and "Load more" button display |  | Pass | Pass | 2016-12-08
[Manage Organization-13] | Click button "Load more" on Organization detail page with 5 events created | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on "Load more" button | 1. Homepage is displayed 2. Organization page is displayed 3. Display Organization detail page - 4 events and "Load more" button display 4. 5 events are displayed and "Loadmore" button disappear |  | Pass | Pass | 2016-12-08
[Manage Organization-14] | Click on an event on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on an event | 1. Homepage is displayed 2. Organization page is displayed 3. Go to Event detail |  | Pass | Pass | 2016-12-08
[Manage Organization-15] | Click on "View more" button on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on "View more" button | 1. Homepage is displayed 2. Organization page is displayed 3. Go to Event detail |  | Pass | Pass | 2016-12-08
[Manage Organization-16] | Order event list by point on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on Order list 5. Choose Point | 1. Homepage is displayed 2. Organization page is displayed 3. Organization detail page is displayed 4. Display Order list: - Other - Point - Ongoing - Closed 5. Event list order by Point |  | Pass | Pass | 2016-12-08
[Manage Organization-17] | Order event list by status "Ongoing" on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on Order list 5. Choose Ongoing | 1. Homepage is displayed 2. Organization page is displayed 3. Organization detail page is displayed 4. Display Order list: - Other - Point - Ongoing - Closed 5. Event list order by status: Ongoing |  | Pass | Pass | 2016-12-08
[Manage Organization-18] | Order event list by status "Closed" on Organization detail page | 1. Login wings.com with registered account 2. Click on Organization tab 3. Click on a Organization 4. Click on Order list 5. Choose Closed | 1. Homepage is displayed 2. Organization page is displayed 3. Organization detail page is displayed 4. Display Order list: - Other - Point - Ongoing - Closed 5. Event list order by status: Closed |  | Pass | Pass | 2016-12-08
[Manage Organization-19] | Check "Report" button on organization detail page when user already reported before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up with many reasons. |  | Pass | Pass | 2016-12-08
[Manage Organization-20] | Check "Send Report" button in Report pop-up | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button 5. Choose 1 reason and click send | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up with many reasons. 5. Pop-up is closed and notice that report successful |  | Pass | Pass | 2016-12-08
[Manage Organization-21] | Check "Report" button in Report pop-up when user already reported before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up with message: [MS31] |  | Pass | Pass | 2016-12-08
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Manage Thread
Back to Test Report
Module Code | Manage Thread | [7 empty] | Pass
Test requirement | This test cases were created to test Manage thread module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
66 | 0 | 2 | 0 | 68 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[Manage Thread-2] | Go to Thread page when login | 1. Login wings.com with registered account 2. Click on Thread tab | 2. Thread page is displayed |  | Pass | Pass | 2016-12-08
[Manage Thread-3] | Check tab focus when user viewing Thread page | 1. Login wings.com with registered account 2. Click on Thread tab | 2. Thread page is displayed and tab focus Thread |  |  | Pass | 2016-12-08
[Manage Thread-4] | View Thread page with no thread when login | 1. Login wings.com with registered account 2. Click on Thread tab | 1. Homepage is displayed 2. Thread page is displayed with no thread |  | Pass | Pass | 2016-12-08
[Manage Thread-5] | View Thread page with 8 threads when login | 1. Login wings.com with registered account 2. Click on Thread tab | 1. Homepage is displayed 2. Thread page is displayed with 10 threads and Load more icon displayed |  | Pass | Pass | 2016-12-08
[Manage Thread-6] | Test Click Load more in event page and with 4 events | 1. Login wings.com with registered account 2. Click on Thread tab | 1. Homepage is displayed 2. Thread page is displayed 4 events and button "Load more" is not displayed |  | Pass | Pass | 2016-12-08
[Manage Thread-7] | View Thread detail | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page |  | Pass | Pass | 2016-12-08
[Manage Thread-8] | Check Thread title on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page with title same with in database |  | Pass | Pass | 2016-12-08
[Manage Thread-9] | Check Thread creator on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page - Display creator name of thread |  | Pass | Pass | 2016-12-08
[Manage Thread-10] | Check Click Thread creator on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Creator name of thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Move to User profile page of creator |  | Pass | Pass | 2016-12-08
[Manage Thread-11] | Check Like button on thread detail page when user did not like this thread before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Like button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Change color of like button and number of like increase 1 |  | Pass | Pass | 2016-12-08
[Manage Thread-12] | Check Like button on thread detail page when user already liked | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Like button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Change color of like button and number of like decrease 1 |  | Pass | Pass | 2016-12-08
[Manage Thread-13] | Check Share button on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Share button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Redirect to confirm share post of facebook |  | Pass | Pass | 2016-12-08
[Manage Thread-14] | Check Thread content on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page - Display content of thread in Content tab |  | Pass | Pass | 2016-12-08
[Manage Thread-15] | Check Thread picture on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Picture tab | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pictures of thread in Pictures tab |  | Pass | Pass | 2016-12-08
[Manage Thread-16] | Check number comment of thread on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page - Display number comment of thread |  | Pass | Pass | 2016-12-08
[Manage Thread-17] | Check all comment of thread on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page - Display all comment of thread |  | Pass | Pass | 2016-12-08
[Manage Thread-18] | Check Send comment on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Write comment and press Enter | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display comment |  | Pass | Pass | 2016-12-08
[Manage Thread-19] | Check Like comment button on thread detail page when user did not like this thread before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Like comment button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Change color of like comment button and number of like increase 1 |  | Pass | Pass | 2016-12-08
[Manage Thread-20] | Check Like button on thread detail page when user already liked | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Like comment button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Change color of like comment button and number of like decrease 1 |  | Pass | Pass | 2016-12-08
[Manage Thread-21] | Check Reply comment button on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Reply comment button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display comment text for user |  | Pass | Pass | 2016-12-08
[Manage Thread-22] | Check Send reply comment on thread detail page | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on Reply comment button 5. Write comment and press Enter | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display sub comment text for user 5. Display reply comment |  | Pass | Pass | 2016-12-08
[Manage Thread-23] | Check "Report" button on thread detail page when user already reported before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up and notice that user already reported |  | Pass | Pass | 2016-12-08
[Manage Thread-24] | Check "Send Report" button in Report pop-up | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button 5. Choose 1 reason and click send | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up with many reasons. 5. Pop-up is closed and notice that report successful |  | Pass | Pass | 2016-12-08
[Manage Thread-25] | Check "Report" button in Report pop-up when user already reported before | 1. Login wings.com with registered account 2. Click on Thread tab 3. Click on a thread 4. Click on "Report" button | 1. Homepage is displayed 2. Thread page is displayed 3. Display thread detail page 4. Display pop-up with message: [MS31] |  | Pass | Pass | 2016-12-08
[Manage Thread-26] | Go to Creat Thread page when login | 1. Login wings.com with registered account 2. Click on Create Thread | 2. Create Thread page is displayed |  | Pass | Pass | 2016-12-08
[Manage Thread-27] | Check upload Thread pictures | 1. Login wings.com with registered account 2. Click on Create Thread 3. Click on upload pictures | 2. Thread page is displayed 3. Pictures is uploaded |  | Pass | Pass | 2016-12-08
[Manage Thread-28] | Check create Thread successful | 1. Login wings.com with registered account 2. Click on Create Thread 3. Fill all information and click Create | 2. Thread page is displayed 3. Thread created and redirect to thread detail |  | Pass | Pass | 2016-12-08
[Manage Thread-29] | Review creator of recent thread created | 1. Login wings.com with registered account 2. Click on Create Thread 3. Fill all information and click Create | 2. Thread page is displayed 3. Thread created and redirect to thread detail - Display name of thread's creator |  | Pass | Pass | 2016-12-08
[Manage Thread-30] | Review date created of recent thread created | 1. Login wings.com with registered account 2. Click on Create Thread 3. Fill all information and click Create | 2. Thread page is displayed 3. Thread created and redirect to thread detail - Display date created of thread's creator |  | Pass | Pass | 2016-12-08
[Manage Thread-31] | Review content of recent thread created | 1. Login wings.com with registered account 2. Click on Create Thread 3. Fill all information and click Create 4. Click on Content tab 5. Click on Pictures tab | 2. Thread page is displayed 3. Thread created and redirect to thread detail 4. Content of thread is displayed 5. Pictures of thread is displayed |  | Pass | Pass | 2016-12-08
[Manage Thread-32] | Go to Edit Thread page | 1. Login wings.com with registered account 2. Click thread tab 3. Click on a created thread 4. Click on Edit Thread | 2. Your Organization page is displayed 3. Created thread page is displayed 4. Edit thread page is displayed |  | Pass |  | 2016-12-08
[Manage Thread-33] | Edit Thread page successful | 1. Login wings.com with registered account 2. Click thread tab 3. Click on a created thread 4. Click on Edit Thread 5. Edit thread and click "Save" button | 2. Thread page is displayed 3. Created thread page is displayed 4. Edit thread page is displayed 5. Edit thread page is closed and move to thread detail |  | Pass | Pass | 2016-12-08
[Manage Thread-34] | Review creator of recent thread edited | 1. Login wings.com with registered account 2. Click thread tab 3. Click on a created thread 4. Click on Edit Thread 5. Edit thread and click "Save" button | 2. Thread page is displayed 3. Created thread page is displayed 4. Edit thread page is displayed 5. Edit thread page is closed and move to thread detail - Display name of thread's creator as before |  | Pass | Pass | 2016-12-08
[Manage Thread-35] | Review content of recent thread edited | 1. Login wings.com with registered account 2. Click thread tab 3. Click on a created thread 4. Click on Edit Thread 5. Edit thread and click "Save" button | 2. Thread page is displayed 3. Created thread page is displayed 4. Edit thread page is displayed 5. Edit thread page is closed and move to thread detail - Display content of thread as edited |  | Pass | Pass | 2016-12-08
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## User Profile
Back to Test Report
Module Code | User profile | [7 empty] | Pass
Test requirement | This test cases were created to test User profile module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
36 | 0 | 0 | 0 | 36 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[User profile-2] | Go to User profile page when login | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information | 1. Display home page 2. Display menu list: - Message - User Information - Organization - Log out 3. Redirect to user information page |  | Pass | Pass | 2016-12-03
[User profile-3] | View other user profile page when login | 1. Login wings.com with registered account 2. ../Profile/AccountTest | 1. Display home page 2. Redirect to Accounttest information page |  | Pass | Pass | 2016-12-03
[User profile-4] | Go to User profile page and check information tab | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information | 1. Display home page 2. Display menu list: - Message - User Information - Organization - Log out 3. Redirect to user information page - All information of user display |  | Pass | Pass | 2016-12-03
[User profile-5] | Go to User profile page and check donation history tab with no record | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on donation history tab | 3. Redirect to user information page 4. Donation history tab is displayed with no record |  | Pass | Pass | 2016-12-03
[User profile-6] | Go to User profile page and check donation history tab with 5 records | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on donation history tab | 3. Redirect to user information page 4. Donation history tab is displayed with 5 records |  | Pass | Pass | 2016-12-03
[User profile-7] | Go to User profile page and search on donation history tab | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on donation history tab 5. Input keyword on searching box | 3. Redirect to user information page 4. Donation history tab is displayed 5. Only event has keyword display on table |  | Pass | Pass | 2016-12-03
[User profile-8] | Go to User profile page and check created thread tab with no record | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information. 4. Click on Created thread | 3. Redirect to user information page 4. Created thread tab is displayed with no record |  | Pass | Pass | 2016-12-03
[User profile-9] | Go to User profile page and check created thread tab with 4 records | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information. 4. Click on Created thread | 3. Redirect to user information page 4. Created thread tab is displayed with no records |  | Pass | Pass | 2016-12-03
[User profile-10] | Go to User profile page and search on created thread tab | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on created thread tab 5. Input keyword on searching box | 3. Redirect to user information page 4. Donation history tab is displayed 5. Only threads which have keyword display on table |  | Pass | Pass | 2016-12-03
[User profile-11] | Go to Change password tab | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab | 3. Redirect to user information page 4. Change password tab is displayed |  | Pass | Pass | 2016-12-03
[User profile-12] | Change password without input old password | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab 5. Input only new password and user name | 3. Redirect to user information page 4. Change password tab is displayed 5 Display message: [MS04] |  | Pass | Pass | 2016-12-03
[User profile-13] | Change password without input user name | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab 5. Input all field without user name | 3. Redirect to user information page 4. Change password tab is displayed 5 Display message: [MS03] |  | Pass | Pass | 2016-12-03
[User profile-14] | Change password without input new password | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab 5. Do not input new password | 3. Redirect to user information page 4. Change password tab is displayed 5 Display message: [MS30] |  | Pass | Pass | 2016-12-03
[User profile-15] | Change password without input new password | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab 5. Input new password and confirm password do not match | 3. Redirect to user information page 4. Change password tab is displayed 5 Display message: [MS31] |  | Pass | Pass | 2016-12-03
[User profile-16] | Change password successful | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on Change password tab 5. Input all field and click | 3. Redirect to user information page 4. Change password tab is displayed 5 Display message: [MS31] |  | Pass | Pass | 2016-12-03
[User profile-17] | Check button Edit Information | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on "Edit Information" button | 3. Redirect to user information page 4. Information field enable to edit |  | Pass | Pass | 2016-12-03
[User profile-18] | Edit Information without change data | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on "Edit Information" button 5. Click on save withou change data | 3. Redirect to user information page 4. Information field enable to edit 5. Infomation field disable to edit and no data chage. - Display pop-up with message: [MS32] |  | Pass | Pass | 2016-12-03
[User profile-19] | Edit Information with change data | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on User Information 4. Click on "Edit Information" button 5. Click on save withou change data | 3. Redirect to user information page 4. Information field enable to edit 5. Infomation field disable to edit and data has been changed as edited - Display pop-up with message: [MS32] |  | Pass | Pass | 2016-12-03
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Donate
Back to Test Report
Module Code | Donate | [7 empty] | Pass
Test requirement | This test cases were created to test Donate module. | [7 empty] | Fail
Tester | DuyTN,TuanHA
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
30 | 0 | 0 | 0 | 30 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[Donate-2] | Go to Donate event page | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button | 1. Display home page 2. Display event detail page 3. Display Donate event page |  | Pass | Pass | 2016-12-04
[Donate-3] | Check payment methods | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Click on Ngan luong payment method | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Display information of payment method |  | Pass | Pass | 2016-12-04
[Donate-4] | Check payment methods | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Click on Banking payment method | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Display information of payment method |  | Pass | Pass | 2016-12-04
[Donate-5] | Check payment methods | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Click on Visa payment method | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Display information of payment method |  | Pass | Pass | 2016-12-04
[Donate-6] | Check donation information | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button | 1. Display home page 2. Display event detail page 3. Display Donate event page - Check donor's name |  | Pass | Pass | 2016-12-04
[Donate-7] | Check donation information | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button | 1. Display home page 2. Display event detail page 3. Display Donate event page - Check donor's mail |  | Pass | Pass | 2016-12-04
[Donate-8] | Check donation information | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button | 1. Display home page 2. Display event detail page 3. Display Donate event page - Check donor's phone number |  | Pass | Pass | 2016-12-04
[Donate-9] | Check donation information | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button | 1. Display home page 2. Display event detail page 3. Display Donate event page - Check event's name |  | Pass | Pass | 2016-12-04
[Donate-10] | Check Click button without input donate content | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field except donate content and click Enter | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Display message: [MS33] |  | Pass | Pass | 2016-12-04
[Donate-11] | Donate success by Ngan luong payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website - Display message successful |  | Pass | Pass | 2016-12-09
[Donate-12] | Donate fail by Ngan luong payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website Redirect to donate fail page |  | Pass | Pass | 2016-12-09
[Donate-13] | Donate success by Banking payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website - Display message successful |  | Pass | Pass | 2016-12-09
[Donate-14] | Donate fail by Banking payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website Redirect to donate fail page |  | Pass | Pass | 2016-12-09
[Donate-15] | Donate success by Visa payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website - Display message successful |  | Pass | Pass | 2016-12-09
[Donate-16] | Donate fail by Visa payment method | 1. Login wings.com with registered account 2. Click on an event 3. Click "Donate" button 4. Input all field and click Donate | 1. Display home page 2. Display event detail page 3. Display Donate event page 4. Redirect to payment website Redirect to donate fail page |  | Pass | Pass | 2016-12-09
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Message
Back to Test Report
Module Code | Message | [7 empty] | Pass
Test requirement | This test cases were created to test Donate module. | [7 empty] | Fail
Tester | DuyTN
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | Untesed
36 | 0 | 0 | 0 | 36 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Display Homepage
[Message-2] | View message page when user have no message yet | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message | 1. Home page is displayed 2. User menu is displayed: - Message - User Information - Organization - Logout 3. Message page is displayed with no message |  | Pass | Pass | 2016-12-04
[Message-3] | View message page when user have 1 message of only 1 other user | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message | 1. Home page is displayed 2. User menu is displayed: - Message - User Information - Organization - Logout 3. Message page is displayed with 1 message of only 1 other user |  | Pass | Pass | 2016-12-04
[Message-4] | View message page when user have 2 messages of only 1 other user | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message | 1. Home page is displayed 2. User menu is displayed: - Message - User Information - Organization - Logout 3. Message page is displayed with message list of only 1 other user |  | Pass | Pass | 2016-12-04
[Message-5] | View message page when user have messages of only 2 other users | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message | 1. Home page is displayed 2. User menu is displayed: - Message - User Information - Organization - Logout 3. Message page is displayed with message list |  | Pass | Pass | 2016-12-04
[Message-6] | Click on a message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside |  | Pass | Pass | 2016-12-04
[Message-7] | Check user who sent message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside - User name of whom sent message same as database |  | Pass | Pass | 2016-12-04
[Message-8] | Check avatar of user whom sent message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside - Avatar of user whom message same as database |  | Pass | Pass | 2016-12-04
[Message-9] | Check title of message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside - Title of message same as database |  | Pass | Pass | 2016-12-04
[Message-10] | Check content of message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside - Content of message same as database |  | Pass | Pass | 2016-12-04
[Message-11] | Check time of message on list message | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list | 3. Message page is displayed with message list 4. Message detail is displayed beside - Sent time of message same as database |  | Pass | Pass | 2016-12-04
[Message-12] | Click on group message box | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on group message box | 3. Message page is displayed with message list 4. Display: - All - Read - Unread |  | Pass | Pass | 2016-12-04
[Message-13] | Reply message successful | 1. Login wings.com with registered account 2. Click on User avatar menu 3. Click on message 4. Click on a message on list 5. Write message on text box and press Enter | 3. Message page is displayed with message list 4. Message detail is displayed beside 5. Message displayed on message content |  | Pass | Pass | 2016-12-04
[Message-14] | Check send message pop-up to other user | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed |  | Pass | Pass | 2016-12-04
[Message-15] | Check receiver name in send message pop-up | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed - Display name of receiver: AccountTest2 |  | Pass | Pass | 2016-12-04
[Message-16] | Check receiver name in send message pop-up | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed - Display name of receiver: AccountTest2 |  | Pass | Pass | 2016-12-04
[Message-17] | Check click Send button in Message pop-up when only input message title | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message 4. Input only title and click Send 5. Click OK | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed 4. Display message [MS34] |  | Pass | Pass | 2016-12-04
[Message-18] | Check click Send button in Message pop-up when only input message content | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message 4. Input only content and click Send 5. Click OK | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed 4. Display message [MS34] |  | Pass | Pass | 2016-12-04
[Message-19] | Check click Send button in Message pop-up when input message title and content | 1. Login wings.com with registered account 2. Go to URL: …/Profile/AccountTest2 3. Click on message 4. Input title and content then click Send 5. Click OK | 1. Home page is displayed 2. User profile page of AccountTest2 is displayed 3. Send message pop-up is displayed 4. Display message [MS34] |  | Pass | Pass | 2016-12-04
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Admin module
Back to Test Report | [8 empty] | Pass
Module Code | Admin Module | [7 empty] | Fail
Test requirement | This test cases were created to test Admin module.
Tester | DuyTN | [7 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
1 | 0 | 141 | 0 | 142
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 53 | Result Firefox version 50 | Test date | Note
Log in
[Admin Module-2] | Test Login panel view | 1. Go to …/Admin.com | 1. Admin Login page is displayed |  | Pass
[Admin Module-3] | Admin login success | 1. Go to …/Admin.com 2. Enter UserName and Password: - admin - 123456 3. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. - "admin" is displayed in user name text box - "••••••••••" is displayed in password text box 3. Admin is logged in
[Admin Module-4] | Admin login without UserName | 1. Go to …/Admin.com 2. Do not input to User name text box and input password 3. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-5] | Admin login with wrong user name | 1. Go to …/Admin.com 2. Input "!!!!!@@@SS" to User name text box | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-6] | Admin login with non-existence user name | 1. Go to …/Admin.com 2. Input "NonExitstance" to User name text box | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-7] | Admin login with wrong user password | 1. Go to …/Admin.com 2. Enter UserName and Password: - adminfail - 12345678 3. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-8] | Admin login without user password | 1. Go to …/Admin.com 2. Enter password and do not enter UserName 4. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-9] | Admin login without user password | 1. Go to …/Admin.com 2. Enter UserName - wingstest01 and do not input user password 3. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-10] | Admin login without UserName and password | 1. Go to …/Admin.com 2. Do not input UserName and password 3. Click on 'Đăng nhập' button | 1. Admin Login page is displayed 2. Display message: MS23
[Admin Module-11] | When user input wrong username and correct password | 1. Enter the admin page 2. Input username and password, then click "Login" button | 1.The admin page is displayed 2. Display error message "Username or Password wrong"
Common module
[Admin Module-13] | Check Admin view | 1. Go to …/Admin.com | 1. Admin Page is displayed with the following list: - Header - Right Side bar - Content details left
[Admin Module-14] | Check Logout button | 1. Go to …/Admin.com 2. Click logout button in Right Slide bar | 1. Admin Page is displayed 2. Log in Page is displayed
[Admin Module-15] | Check Slidebar toggle button | 1. Go to …/Admin.com 2. Click Sidebar toggle button in Right Slide bar 3. Click Sidebar toggle button in Right Slide bar | 1. Admin Page is displayed 2. Sidebar is hidden 3. Siderbar is showed
[Admin Module-16] | Test Admin when admin click Slidebar toggle button | 1. Enter the admin page 2. Click Sidebar toggle button in Right Slide bar 3. Click Sidebar toggle button in Right Slide bar | 1. Admin Page is displayed 2. Sidebar is hidden 3. Siderbar is showed
User Management module
[Admin Module-18] | Check User button in sidebar | 1. Go to …/Admin.com 2. Click User button in Right Slide bar 3. Click Dashboard button in User menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + User list 3. Content about dashboard of user is displayed
[Admin Module-19] | Check User list button in User menu | 1. Go to …/Admin.com 2. Click User button in Right Slide bar 3. Click User list button in User menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + User list 3. Content of User list is displayed
[Admin Module-20] | Check View button in Users list table | 1. Go to …/Admin.com 2. Click User button in Right Slide bar 3. Click User list button in User menu 4. Select a user and click View button | 1. Admin Page is displayed 2. Dropdowlist is displayed with: 3. Content of Users list is displayed 4. Userprofile Page is displayed
[Admin Module-21] | Check Active User button | 1. Enter the Userprofle Page 2. Click tab Profile 3. Click Active button (on De-active user) | 1. Userprofile Page is displayed 2. Profile of user is displayed 3. User status is changed to Active
[Admin Module-22] | Check Deactive User button | 1. Enter the Userprofle Page 2. Click tab Profile 3. Click Deactive button (on active user) | 1. Userprofile Page is displayed 2. Profile of user is displayed 3. User status is changed Deactive
[Admin Module-23] | Test Active/Deactive User in same time | 1. Enter the Userprofle Page 2. Click tab Profile 3. Click Active/Deactive button 2 timé | 1. Userprofile Page is displayed 2. Profile of user is displayed 3. User is actived/Deactived and return Users list Page
EventManagement module
[Admin Module-25] | Check Event button in sidebar | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Dashboard button in User menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Event list + Event type
[Admin Module-26] | Check Events List button in Event menu | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Events list button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Events list + Event type 3. Content about Events lists of Event is displayed
[Admin Module-27] | Check Events List when have no data yet | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Events list button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Events list + Event type 3. No data is displayed on Events lists of Event is displayed
[Admin Module-28] | Check Events List when have 2 events | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Events list button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Events list + Event type 3. 2 events displayed on Events lists of Event is displayed
[Admin Module-29] | Check Events List when have 12 events | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Events list button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Events list + Event type 3. 12 events displayed on Events lists of Event is displayed
[Admin Module-30] | Check View button in Event type table | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Event type button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed 3. Event type list is displayed
[Admin Module-31] | Check Active Event button | 1. Enter the admin page 2. Click on Event List on Event tab menu 3. Click Active button (on De-active Event) | 1. Enter the admin page 2. Click on Event List on Event tab menu 3. Event status is changed to Active
[Admin Module-32] | Check Deactive Event button | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click View button 4. Click Deactive button (on active Event) | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click View button 4. Event status is changed Deactive
[Admin Module-33] | Check View button in Event list table | 1. Enter the admin page 2. Click Event button in Right Slide bar 3. Click Event list button in Event menu 4. Select a Event and click View button | 1. Admin Page is displayed 2. Dropdowlist is displayed 3. Content of Events list is displayed 4. Event detail Page is displayed.
ThreadManagement module
[Admin Module-35] | Check Thread button in sidebar | 1. Login on admin page 2. Click Thread button in Right Slide bar | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list
[Admin Module-36] | Check Dashboard button in Thread menu | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Dashboard button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. Dashboard of Thread is displayed
[Admin Module-37] | Check 0 record on Dashboard of thread | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Dashboard button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. Display no record
[Admin Module-38] | Check 10 record on Dashboard of thread | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Dashboard button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. Display 10 records on Dashboard
[Admin Module-39] | Check 20 record on Dashboard of thread | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Dashboard button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. Display 10 records on Dashboard and 2 pages
[Admin Module-40] | Check Thread List button in Thread menu | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Thread list button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. Content about Thread lists of Thread is displayed
[Admin Module-41] | Check Thread List when have no data yet | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Thread list button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. No data is displayed on Thread lists of Thread is displayed
[Admin Module-42] | Check Thread List when have 2 events | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Thread list button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. 2 threads displayed on Thread lists of Event is displayed
[Admin Module-43] | Check Thread List when have 10 events | 1. Login on admin page 2. Click Thread button in Right Slide bar 3. Click Thread list button in Thread menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Thread list 3. 2 thread displayed on Thread lists of Thread is displayed
[Admin Module-44] | Check Active Thread button | 1. Enter the admin page 2. Click on Thread List on Thread tab menu 3. Click Active button (on De-active Event) | 1. Enter the admin page 2. Click Thread button in Right Slide bar 3. Thread status is changed to Active
[Admin Module-45] | Check Deactive Thread button | 1. Enter the admin page 2. Click on Thread List on Thread tab menu 3. Click Deactive button (on active Event) | 1. Enter the admin page 2. Click on Thread List on Thread tab menu 3. Thread status is changed Deactive
Admin login with OrganizationManagement module
[Admin Module-47] | Check List Organization button in sidebar | 1. Login on admin page 2. Click Thread button in Right Slide bar | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list + Request list
[Admin Module-48] | Check Dashboard button in Thread menu | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Dashboard button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list + Request list 3. Organization dashboard is displayed
[Admin Module-49] | Check 0 record on Dashboard of Organization | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Dashboard button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list + Request list 3. Display no record
[Admin Module-50] | Check 20 record on Dashboard of Organization | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Dashboard button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list + Request list 3. Display 10 records on Dashboard and 2 pages
[Admin Module-51] | Check 20 record on Dashboard of Organization | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Dashboard button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list + Request list 3. Display 20 records on Dashboard and 2 pages
[Admin Module-52] | Check Organization List when have no data yet | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Organization list button in Event menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list 3. No data is displayed on Organization lists of Organization is displayed
[Admin Module-53] | Check Organization List when have 2 organization | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Organization list button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list 3. 2 organizations displayed on Organization lists of Organization is displayed
[Admin Module-54] | Check Organization List when have 10 events | 1. Login on admin page 2. Click Organization button in Right Slide bar 3. Click Organization list button in Organization menu | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + Dashboard + Organization list 3. 2 organizations displayed on Organization lists of Thread is displayed
[Admin Module-55] | Check Active Organization button | 1. Enter the admin page 2. Click on Organization List on Organization tab menu 3. Click Active button (on De-active Event) | 1. Enter the admin page 2. Click Organization button in Right Slide bar 3. Organization status is changed to Active
[Admin Module-56] | Check Deactive Organization button | 1. Enter the admin page 2. Click on Organization List on Organization tab menu 3. Click Deactive button (on active Event) | 1. Enter the admin page 2. Click on Organization List on Thread tab menu 3. Organization status is changed Deactive
[Admin Module-57] | Check Report list in sidebar | 1. Enter the admin page 2. Click Report button in Right Slide bar | 1. Admin Page is displayed 2. Dropdowlist is displayed with: + User + Event + Thread + Organization
[Admin Module-58] | Check User Report list in sidebar when have no data | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on User | 3. Display list user reported and no record on it
[Admin Module-59] | Check User Report list in sidebar when 10 records | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on User | 3. Display list user reported and 10 records display on it
[Admin Module-60] | Check User Report list and click confirm | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on User 4. Chose 1 record and click "Confirm" | 3. Display list user reported and 10 records display on it 4. User has been banned and report status has been changed
[Admin Module-61] | Check User Report list and click Cancel | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on User 4. Chose 1 record and click "Cancel" | 3. Display list user reported and 10 records display on it 4. User has been banned and report status has been changed
[Admin Module-62] | Check Event Report list in sidebar when have no data | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Event | 3. Display list event reported and no record on it
[Admin Module-63] | Check Event Report list in sidebar when 10 records | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Event | 3. Display list event reported and 10 records display on it
[Admin Module-64] | Check Event Report list and click confirm | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Event 4. Chose 1 record and click "Confirm" | 3. Display list event reported and 10 records display on it 4. Event has been banned and report status has been changed
[Admin Module-65] | Check Event Report list and click Cancel | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Event 4. Chose 1 record and click "Cancel" | 3. Display list event reported and 10 records display on it 4. Event has been banned and report status has been changed
[Admin Module-66] | Check Thread Report list in sidebar when have no data | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Thread | 3. Display list thread reported and no record on it
[Admin Module-67] | Check Thread Report list in sidebar when 10 records | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Thread | 3. Display list thread reported and 10 records display on it
[Admin Module-68] | Check Thread Report list and click confirm | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Thread 4. Chose 1 record and click "Confirm" | 3. Display list thread reported and 10 records display on it 4. Thread has been banned and report status has been changed
[Admin Module-69] | Check Thread Report list and click Cancel | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Thread 4. Chose 1 record and click "Cancel" | 3. Display list thread reported and 10 records display on it 4. Thread has been banned and report status has been changed
[Admin Module-70] | Check Organization Report list in sidebar when have no data | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Organization | 3. Display list organization reported and no record on it
[Admin Module-71] | Check Organization Report list in sidebar when 10 records | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Organization | 3. Display list organization reported and 10 records display on it
[Admin Module-72] | Check Organization Report list and click confirm | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Organization 4. Chose 1 record and click "Confirm" | 3. Display list thread reported and 10 records display on it 4. Organization has been banned and report status has been changed
[Admin Module-73] | Check Organization Report list and click Cancel | 1. Enter the admin page 2. Click Report button in Right Slide bar 3. Click on Organization 4. Chose 1 record and click "Cancel" | 3. Display list thread reported and 10 records display on it 4. Organization has been banned and report status has been changed

## List (hidden)
Pass
Fail
N/A
Untested