## Function logs
Fuction Log |  |  |  |  | Done
Pending
Inprogress
Stt | Group | Function | Status | Note
1 | Login | Login | Done
2 |  | Login with Facebook | Done
3 |  | Logout | Done
4 |  | Register | Done
5 |  | Forgot Password | Done
6 |  | Verify email | Done
7 | Home | View top four Events | Done
8 |  | View top four Threads | Pending | 90%
9 |  | View top three Organizations | Done
10 | Event | Create event | Done
11 |  | View Event List | Done
12 |  | Load more events | Done
13 |  | Search event | Done
14 |  | Sort event | Inprogress | 90%
15 |  | Show event follow event type | Done
16 |  | View an event's detail | Done
17 |  | Edit an event
18 | Thread | Create thread | Done
19 |  | View thread List | Done
20 |  | Load more threads | Done
21 |  | Search thread | Done
22 |  | View a thread detail | Done
23 |  | Edit an thread
24 | Organization | Create organization | Done
25 |  | View organization List | Done
26 |  | Load more organization | Done
27 |  | Search organization | Done
28 |  | View a organization detail | Done
29 |  | Edit an organization | Done
30 | User | View detail information | Done
31 |  | Edit information
32 | Search | Search user | Done
33 |  | Search event | Done
34 |  | Search thread | Done
35 |  | Search organization | Done
36 | Donate | View information before donating
37 |  | Donate using NganLuong
38 | Report | Report Event
39 |  | Report Thread
40 |  | Report Organization
41 |  | Report User
42 | Chat | Chat Room in event detail | Done
43 |  | Message | Done
44 | About us | View detail information of website's developer
45 | Contact | Send message to admin
46 | Notification | Notice
47 | Common | like | Done
48 |  | follow
49 |  | share
50 |  | comment | Done
51 |  | delete comment
52 | Rank | ranking organization
53 |  | ranking user
54 | Admin | Admin login | Done
55 |  | Admin logout | Done
56 |  | Admin forgot password
57 | Manage User | View user's dashboard
58 |  | Active/Inactive user's account
59 |  | Search user
60 | Manage Event | View event's dashboard
61 |  | Approve event
62 |  | Change event status (active/inactive)
63 | Manage thread | View thread's dashboard
64 |  | Approve thread
65 |  | Change thread status (active/inactive)
66 | Manage report | View report's dashboard
67 |  | View report detail
68 |  | Change report's status
69 | Manage mailbox | View received message
70 | Manage donate | View donate's dashboard